## Sheet1
Feature | Description | State | Duration
Products Component | Show list of products in the home page | Open | 2 | Time | 35 | hrs
Filter Component | Filter products based on their sizes and sort by price | Open | 2 | Rate | 30 | USD/Hr
Cart Component | Show selected items in the cart on the right sidebar | Open | 3 | Cost | 1050
Add Animation | Animated products list and adding to cart | Open | 2
Add Modal | Show modal when user click on a product | Open | 2
Checkout Form | Show checkout form to get byer's data | Open | 2
Products Backend | Create a simple backend to send products to frontend | Open | 3
Add Redux | Create store, initial state and reducer and redux devtools | Open | 2
Add Redux To Products | Move products state to redux | Open | 3
Add Redux To Filter | Move filter state to redux | Open | 3
Add Redux To Cart | Move cart state to redux | Open | 3
Create Order | Handle frontend and backend of creating an order | Open | 3
Add Admin Section | Use react-router to create two routes for Home and Admin | Open | 2
Publish on Heroku | Create Mongodb Atlas database and publish Heroku app | Open | 3